## Chart 1
Start Date | End Date | Description | Duration
2023-03-01 | 2023-03-04 | Project Planning and Task Assigning | 3
2023-03-04 | 2023-03-11 | Basic UI and HTML set up | 7
2023-03-11 | 2023-03-14 | Set Facial Inputs and Python connections | 3
2023-03-14 | 2023-03-17 | Created local server and database | 3
2023-03-17 | 2023-03-20 | Trained and create Face detection model | 3
2023-03-20 | 2023-03-27 | Final Touches and testing | 7
|  |  |  | Key | Colour
Development
Planning
Testing
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]